Bonn Agreement Action Plan 2016-2019

Introduction

The Greater North Sea and its Approaches are one of the world’s busiest international shipping areas. Increasing traffic densities, transportation of hazardous and noxious substances, larger ship sizes, offshore oil and gas activities, marine renewables and other human uses require close international cooperation to prevent and respond to pollution by oil and other harmful substances. Notwithstanding the Bonn Agreement framework for prevention, preparedness and response, accidental and illegal pollution of the marine environment remains a threat to the Greater North Sea and its Approaches. Lessons learned from more than 45 years operational, technical and scientific work of the Bonn Agreement show that efficient international cooperation is essential in dealing with such threats.

This Bonn Agreement Action Plan (BAAP) therefore sets out Strategic Aims, Operational Objectives and Actions which aim at strengthening the protection of the coastal and marine environment and ultimately achieving the Bonn Agreement’s Vision of “A Greater North Sea and its Approaches free from accidental and illegal pollution from both shipping and other maritime activities”.

The first BAAP was agreed by the Ministerial Meeting of the Bonn Agreement in Dublin, Ireland on 24 November 2010 and has been updated every three years since. It provides a guide and focus to the work of the Bonn Agreement, as well as specific measurable actions and targets, which will be jointly implemented and achieved in the period from 2016-2019. The BAAP acknowledges the need to maintain well established systems and to continue work in hand necessary to continue the operational nature of the Agreement. At the same time, opportunities to enhance these efforts and to develop new directions are articulated.

Vision

The Vision of the Bonn Agreement is of:

A Greater North Sea and its Approaches free from accidental and illegal pollution from shipping, offshore oil and gas operations and other maritime activities

The Greater North Sea and its Approaches support diverse and productive ecosystems that are essential for the daily lives of millions of people. They contain some of the busiest shipping lanes in the world. The vision of the Bonn Agreement is therefore to minimise, as far as practically possible, the threat of pollution from accidental and illegal pollution from both ships and other maritime activities.

To achieve its Vision the Bonn Agreement has agreed the following Strategic Aims:

Strategic Aims

A. 	Prevention of illegal or accidental pollution by collaboration and collective contribution to enforcement of maritime pollution rules and standards

Despite the wide range of measures taken in recent years, illegal and accidental pollution remains a threat for the Greater North Sea and its Approaches. Rules and standards, such as the designation of the North Sea as a Special Area under MARPOL Annex I, will not be effective unless properly enforced. Collaboration in pollution prevention and effective enforcement of international maritime pollution rules and standards are major tools in safeguarding the marine environment.

B. 	Promotion and establishment of efficient emergency preparedness

International and European obligations are in place to ensure that North Sea States are prepared to respond in the event of pollution incidents or to a threat of pollution, including by global protocols and regional joint responsibility zones. Cooperation between contracting parties, with other regional and international organisations is needed to identify synergies and avoid duplication. Appropriate knowledge, planning, training and operational testing of emergency systems are needed to ensure effective preparedness. The planning of counter pollution measures should take into account the best available environmental advice. Contracting Parties may recommend, based on inter alia regional risk assessment studies, a minimum level of national and/or sub regional response capacity, leaving the decision on the preparedness level to the individual contracting parties.

C. 	Organisation of optimum response capacities

Despite all efforts to increase maritime safety there will always be the risk of incidents. A combination of growing levels of maritime transportation and other human activities, transportation of hazardous and noxious cargos and offshore oil and gas operations are leading to increasing risks for the marine environment. Contracting Parties have already put considerable resources into adequate response capacities. To further improve efficiency, not least in financial terms, the further development of response capacities should be based on risk assessments, gap analysis and regional and sub-regional approaches. Coordinated research and development programmes should be promoted to ensure counter-pollution measures are executed with best available techniques and equipment and that decision making processes are supported with the best available knowledge, methods and supportive tools.

D.	Ensure the organisation is fit for purpose in a changing operational environment

- In recent years there have been a number of changes to the threats in the Greater North Sea and its wider Approaches, for example, a reduction in the number of operational oil spills and an increase in the development of renewable energy. This means that the operational environment is changing. In order to ensure that the Bonn Agreement is fit for purpose an evaluation of its role should be undertaken so its mandate can be renewed at the Ministerial level.

To achieve its Strategic Aims the Bonn Agreement has agreed the following Operational Objectives:

Operational Objectives:

Operational Objectives in relation to Strategic Aim A (prevention):

A.1	To undertake adequate surveillance of shipping and other potential polluting activities in the Greater North Sea and its Approaches and ensure efficient reporting of observations in the Bonn Agreement zones of responsibility;

A.2	To provide authorities and aircrew with up to date information on the planning and conduct of counter-pollution flights, also ad-hoc flight operations, within the Bonn Agreement area;

A.3	To ensure efficient gathering of evidence in the case of pollution incidents and close cooperation with investigators and prosecutors on enforcement of maritime pollution rules and standards in the Greater North Sea and its Approaches;

A.4	To communicate and disseminate information on risks and prevention of illegal and accidental pollution to the public and expert level;

A.5	To ensure effective systems for early notification on incidents that may lead to possible oil and HNS spills in order to allow the member states to employ preventing measures.

Operational Objectives in relation to Strategic Aim B (preparedness):

B.1	To support and promote common understanding of the appropriate way to respond to maritime emergencies and ensure awareness of national and regional contingency systems and strategies, encompassing the various elements of response activities;

B.2	To maintain training of response staff and cooperation between combating units of the Contracting Parties and promote the preparedness for efficient multinational combating operations, including system for host nation support and places of refuge;

B.3	To ensure that national approaches to response action are consistent and properly coordinated to safeguard the marine environment and that priorities are established on the most appropriate basis;

B.4	To cooperate with neighbouring countries and maritime regions, and with other regional and international organisations, in order to identify synergies and avoid duplication;

B.5	To continue to evolve preparedness based on environmental risk analysis to keep up with the changing maritime risk

B.6	To discuss in BONN the recommended minimum level of response capacity based on environmental risk assessment studies.

Operational Objectives in relation to Strategic Aim C (response):

C.1	To ensure that Contracting Parties have clear understanding of the ways in which the others respond to incidents, in order to promote the development of best practice;

C.2	To maintain and keep up to date common operational approaches to pollution incidents and promote the use of appropriate response strategies;

C.3	To undertake, through all appropriate financing, coordinated research and development programmes on detection and response technologies, equipment and other operational means and on decision-making support studies and tools;

C.4	To ensure that balance of resources is maintained for response work in the Greater North Sea and its Approaches, based on risk-assessments.

C.5	To support exchange of response experts between BONN and other Regional Agreements;

Operational Objectives in relation to Strategic Aim D (Organisation):

D.1	To review the changing strategic and operational environment and challenges for the organisation:

- taking into account the regional risk the assessment carried out in the BE-AWARE I and II projects;

- new activities and challenges, e.g. offshore wind farms, Hazardous and Noxious Substances, MARPOL, marine spatial planning, etc.;

D.2	To consider the mandate of the organisation and any changes needed to meet the changing operational environment in the Greater North Sea and its Wider Approaches;

D.3	To renew the mandate of the organisation at the ministerial level;

Actions

To achieve its Operational Objectives, the Bonn Agreement has agreed the following Actions; new actions have been identified with an asterisk (*) to differentiate them from on-going work:

Actions in relation to Strategic Aim A (Prevention):

A.1.1	Execute aerial and satellite surveillance operations, including national flights, regional flights, Tour d’Horizon flights and CEPCO/SuperCEPCO flights, to detect, investigate, gather evidence and monitor spillage of oil and other harmful substances, taking into account strategic surveillance needs;

A.1.2	Consider coverage and efficiency of aerial surveillance and analyse strategically surveillance needs, inter alia based on an evaluation of existing data sets of detections of observed oil pollution and other substances, and develop minimum recommendations on standards for aerial surveillance in the Bonn Agreement area;

A.1.3	Maintain an efficient standard of monitoring and reporting, utilising SafeSeaNet, and use the system to report detected pollution to the Bonn Agreement;

A.1.4	In cooperation with the European Maritime Safety Agency make optimum use of satellite images, e.g. through CleanSeaNet, in order to follow-up to first alert of detection of possible pollution through aerial surveillance;

A.1.5	Strengthen and expand cooperation on the detection and observation of offences in relation to MARPOL Annexes and the contribution to enforcement;

A.1.6*	Investigate the development of standards for the utilisation of UAV’s in aerial surveillance;

A.2.1	Maintain and keep up to date the Aerial Operations Handbook;

A.2.2	Maintain the online version of the Bonn Agreement Oil Appearance Code (BAOAC), including photo atlas, for air crew and expert level as part of the Bonn Agreement website redevelopment;

A.3.1	Strengthen cooperation with the North Sea Network of Investigators and Prosecutors (NSN) and jointly:

a.	maintain and keep up to date the North Sea Manual on Maritime Oil Pollution Offences;

b.	hold meetings on areas of interest, such as progress to court for HNS spills;

A.3.2	Assess how the long-term funding and organisation of the Bonn Agreement Oil Spill Identification Network (OSINET), preferably under the EU umbrella, in order to:

a. 	improve knowledge and experience of relevant laboratories, including through inter-calibration exercises; and

b.	keep up to date analytical procedures and reference methods, including for  oil sampling at sea and during Port State Control;

A.3.3*	Investigate the possibilities for co-operation with HELCOM groups, and other sub regional agreement where appropriate, to find ways for increased efficiency in cooperation between the regional agreements.

A.4.1	Maintain and keep up to date the Bonn Agreement website and dissemination of electronic publications (i.e. manuals, handbooks and reports).

A.4.2*	Support a process through IMO-MEPC for the review of discharge conditions under MARPOL Annex II in order to further reduce discharge rates of cargo residues and tank washings of high viscosity and persistent floating products.

A.4.3*	Investigate with European Port Association to increase Port Reception Facilities for discharging cargo residues especially chemicals;

A.4.4*	Highlight the results of BE-AWARE Projects, in relation to Traffic Separation Schemes, Vessel Traffic Services and E-Navigation, to authorities responsible for risk reduction measures

A.4.5	Implement the Bonn Agreement Communication Strategy,

A.5.1*	Review the existing recommendations for notification with relation to drifting objects, and make necessary adjustments.

Actions in relation to Strategic Aim B (Preparedness):

B.1.1	Maintain and update the different Chapters of the Bonn Agreement Counter Pollution Manual, including integrating the new routines related to the new EU Emergency Response Coordination Centre (ERCC) and the response capacities of EMSA (i.e. pollution response vessels, specialised equipment, MAR-ICE Service, etc.);

B.1.2*	Step up planning and coordination at regional and European level by dedicating national capacities and expertise to the European Emergency Response capacity ("voluntary pool").

B.1.3	Promote information exchange on potentially polluting wrecks;

B.1.4	Strengthen exchange of information on places of refuge taking into account the EU Operational Guidelines;

B.1.5	Enhance readiness to receive/offer/transit international assistance making use of the EU Host Nation Support Guidelines

B.2.1*	Plan and undertake regional and sub-regional operational exercises and training, taking into account strategic needs e.g. response in wind farms;

B.2.2	Organise a joint operational combat exercise (BONNEX DELTA), in relation to regional strategic training needs;

B.2.3	Maintain a system for graduated joint exercises to test and train cooperation in combating spillages;

B.3.1	Promote the development of national environmental advice systems and related exchanges of information – develop and identify best-practice for Contracting Parties’ environmental advice systems and priorities for responses to incidents giving particular attention to cross-boundary cooperation;

B.4.1	Maintain information exchange with other regional and international organisations, in particular the EMSA, EPPR (Arctic Council), HELCOM, IMO, OSPAR Commission and REMPEC, or other relevant fora such as the North Atlantic Coast Guard Forum, through attendance in Inter-Secretariat meetings, reciprocal reporting to the OSPAR Commission and, as appropriate, reciprocal attendance of key meetings

B.4.2	Strengthen cooperation with the OSPAR Commission and other international organisations involved in protecting the marine environment from pollution from shipping, offshore oil and gas operations and other maritime activities, taking into account the obligations under the Marine Strategy Framework and the Water Framework Directives;

B.4.3	Explore with Contracting Parties of the Lisbon Agreement how more permanent arrangement can be made for effective cooperation in dealing with issues covered by the Bonn Agreement in the Atlantic coastal waters south of the North Sea Area;

B.4.4	Contribute to strengthening international implementation of the OPRC and its HNS Protocol.

B.5.1	Explore and exchange information on provision of reception facilities for oil or other materials recovered from accidents

B.5.2*	Consider future developments (2030) in maritime activities and the potential impact on the Bonn Agreement. This consideration would look at activities; inter alia, the increasing size of vessels, renewable energy, offshore oil and gas industry, LNG fuels and port expansions;

B.6.1*	Exchange information on national levels of response capacity taking into account the results of BE-AWARE.

Actions in relation to Strategic Aim C (Response):

C.1.1	Exchange information on lessons learned from incidents;

C.2.1	Maintain an efficient system for the management of requests for and offers of assistance utilising the Marine Pollution Common Emergency Communication and Information System (CECIS MP) of the European Commission;

C.2.2	Maintain and keep up to date joint response plans to maritime incidents (DENGERNETH Plan, MANCHEPLAN, Quadripartite Zone Plan, NORBRIT Plan, UK and Ireland MOU);

C.2.3	Maintain information exchange on national wildlife response systems and include a Chapter on wildlife response in the Counter Pollution Manual;

C.2.4*	Develop specific response strategies for pollution incidents in relation to new maritime activities (e.g. wind farms)

C.3.1*	Initiate research and development: on accidents at night, in bad visibility and under bad weather conditions; accidents involving heavy oil and chemical accidents, possibly through externally funded projects; on response technologies, equipment and other operational means, in particular on integrated surveillance sensors, oil spill drift forecasting and response technologies

C.3.2*	Promote research on HNS response technologies and operational decision support tools taking into account lessons learned from past projects;

C.4.1*	Follow up of the response actions of the BE-AWARE I and II projects in line with the Implementation Plan.

C.4.2*	Consideration and development of a project proposal for a regional risk assessment for HNS;

C.5.1*	Promote networking with other Regional Agreements through the exchange of experts and observers in response operations;

Actions in relation to Strategic Aim D (Organisation):

D.1.1*	Review the political, economic, organisational, technical and legal changes being faced by the organisation, based on the outcome of a SWOT analysis, taking into account the outcomes of the BE-AWARE Projects;

D.2.1*	Review and, if necessary, consider updates to the Bonn Agreement mandate, including inter alia consideration of the scope and coverage of the Bonn Agreement;

D.3.1*	Organise a Bonn Agreement Ministerial meeting in 2019 to mark the 50th anniversary of the agreement, Review and consider the Bonn Agreement’s mandate based on the outcome of the SWOT analysis.

Implementation

To deliver the Bonn Agreement Action Plan the Bonn Agreement has agreed to adopt the accepted lead country approach and to incorporate Actions within the annual Programmes of Work. For Actions that fall outside the provisions of the Bonn Agreement general budget detailed costing estimates should be proposed. All possible funding instruments will be explored including special voluntary one-off contributions by individual (or combinations of) Contracting Parties, and funding instruments made available by the European Union.

Review

The Bonn Agreement will review the Action Plan in 2019.

Annex 2

Actions in relation to Strategic Aim A (Prevention):

| Product | Description | Target date | Lead | Progress | Status |
| --- | --- | --- | --- | --- | --- |
| A.1.1 | Execute aerial and satellite surveillance operations, including national flights, regional flights, Tour d’Horizon flights and CEPCO/SuperCEPCO flights, to detect, investigate, gather evidence and monitor spillage of oil and other harmful substances, taking into account strategic surveillance needs; | Activities undertaken throughout the year | Contracting Parties |  |  |
| A.1.2 | Consider coverage and efficiency of aerial surveillance and analyse strategically surveillance needs, inter alia based on an evaluation of existing data sets of detections of observed oil pollution and other substances, and develop minimum recommendations on standards for aerial surveillance in the Bonn Agreement area; | 2019 | The Netherlands and the European Union (for options on streamlining maritime surveillance e.g. for fisheries and pollution purposes) |  |  |
| A.1.3 | Maintain an efficient standard of monitoring and reporting, utilising SafeSeaNet, and use the system to report detected pollution to the Bonn Agreement; | Activities undertaken when required | Contracting Parties |  |  |
| A.1.4 | In cooperation with the European Maritime Safety Agency make optimum use of satellite images, e.g. through CleanSeaNet, in order to follow-up to first alert of detection of possible pollution through aerial surveillance; | Activities undertaken when required | Contracting Parties |  |  |
| A.1.5 | Strengthen and expand cooperation on the detection and observation of offences in relation to MARPOL Annexes and the contribution to enforcement; | On-going | Contracting Parties/NSN |  |  |
| A.1.6 | Investigate the development of standards for the utilisation of UAV’s in aerial surveillance | 2019 | NL, BE and DE |  |  |
| A.2.1 | Maintain and keep up to date the Aerial Operations Handbook. | Annually at OTSOPA | Norway |  |  |
| A.2.2 | Maintain the online version of the Bonn Agreement Oil Appearance Code (BAOAC), including photo atlas, for air crew and expert level as part of the Bonn Agreement website redevelopment; | Activities undertaken when required | France |  |  |
| A.3.1 | Strengthen cooperation with the North Sea Network of Investigators and Prosecutors (NSN) and jointly: a. maintain and keep up to date the North Sea Manual on Maritime Oil Pollution Offences; b. hold meetings on areas of interest, such as progress to court for HNS spills; | 2016/2017 | United Kingdom Netherlands |  |  |
| A.3.2 | Assess how the long-term funding and organisation of the Bonn Agreement Oil Spill Identification Network (OSINET), preferably under the EU umbrella, in order to: a. improve knowledge and experience of relevant laboratories, including through inter-calibration exercises; and b. keep up to date analytical procedures and reference methods, including for oil sampling at sea and during Port State Control; | Annually | Germany |  |  |
| A.3.3 | Investigate the possibilities for co-operation with HELCOM groups, and other sub regional agreement where appropriate, to find ways for increased efficiency in cooperation between the regional agreements | On-going | CPs in HELCOM and Secretariat |  |  |
| A.4.1 | Maintain and keep up to date the Bonn Agreement website and dissemination of electronic publications (i.e. manuals, handbooks and reports) | Activity undertaken when required | Secretariat |  |  |
| A.4.2* | Support a process through IMO-MEPC for the review of discharge conditions under MARPOL Annex II in order to further reduce discharge rates of cargo residues and tank washings of high viscosity and persistent floating products | Activity undertaken when required | All Contracting Parties |  |  |
| A.4.3* | Investigate with European Port Association to increase Port Reception Facilities for discharging cargo residues especially chemicals | 2019 | Sweden and The Netherlands |  |  |
| A.4.4* | Highlight the results of BE-AWARE Projects, in relation to Traffic Separation Schemes, Vessel Traffic Services and E-Navigation, to authorities responsible for risk reduction measures | Activity undertaken when required | All Contracting Parties | Ireland, Norway and NL have had workshops |  |
| A.4.5 | Implement the Bonn Agreement Communication Strategy | 2016, 2017, 2018 | Secretariat |  |  |
| A.5.1* | Review the existing recommendations for notification with relation to drifting objects, and make necessary adjustments. | 2017 | Norway |  |  |

Actions in relation to Strategic Aim B (Preparedness):

| Product | Description | Target date | Lead | Progress | Status |
| --- | --- | --- | --- | --- | --- |
| B.1.1 | Maintain and update the different Chapters of the Bonn Agreement Counter Pollution Manual, including integrating the new routines related to the new EU Emergency Response Coordination Centre (ERCC) and the response capacities of EMSA (i.e. pollution response vessels, specialised equipment, MAR-ICE Service, etc.). | Activity undertaken when required | Secretariat and Contracting Parties |  |  |
| B.1.2* | Step up planning and coordination at regional and European level by dedicating national capacities and expertise to the European Emergency Response capacity ("voluntary pool") | Activity undertaken when possible | Contracting Parties |  |  |
| B.1.3 | Promote information exchange on potentially polluting wrecks | On-going | Contracting Parties |  |  |
| B.1.4 | Strengthen exchange of information on places of refuge taking into account the EU Operational Guidelines; | On-going | EU, United Kingdom, Norway and France |  |  |
| B.1.5 | Enhance readiness to receive/offer/transit international assistance making use of the EU Host Nation Support Guidelines | On-going | EU and Norway |  |  |
| B.2.1* | Plan and undertake regional and sub-regional operational exercises and training, taking into account strategic needs e.g. response in wind farms; | 2017 2018 2019 | Contracting Parties |  |  |
| B.2.2 | Organise a joint operational combat exercise (BONNEX DELTA), in relation to regional strategic training needs | 2017 2019 | Norway Germany |  |  |
| B.2.3 | Maintain a system for graduated joint exercises to test and train cooperation in combating spillages | On-going | Denmark |  |  |
| B.3.1 | Promote the development of national environmental advice systems and related exchanges of information – develop and identify best-practice for Contracting Parties’ environmental advice systems and priorities for responses to incidents giving particular attention to cross-boundary cooperation | On-going | United Kingdom |  |  |
| B.4.1 | Maintain information exchange with other regional and international organisations, in particular the EMSA, EPPR (Arctic Council), HELCOM, IMO, OSPAR Commission and REMPEC, or other relevant fora such as the North Atlantic Coast Guard Forum, through attendance in Inter-Secretariat meetings, reciprocal reporting to the OSPAR Commission and, as appropriate, reciprocal attendance of key meetings. | On-going | Secretariat Chair of OTSOPA |  |  |
| B.4.2 | Strengthen cooperation with the OSPAR Commission and other international organisations involved in protecting the marine environment from pollution from shipping, offshore oil and gas operations and other maritime activities, taking into account the obligations under the Marine Strategy Framework and the Water Framework Directives; | Relevant committee dates | The Netherlands and Belgium |  |  |
| B.4.3 | Explore with Contracting Parties of the Lisbon Agreement how more permanent arrangement can be made for effective cooperation in dealing with issues covered by the Bonn Agreement in the Atlantic coastal waters south of the North Sea Area; | On-going | EU, Belgium and France |  |  |
| B.4.4 | Contribute to strengthening international implementation of the OPRC and its HNS Protocol. | On-going | Sweden |  |  |
| B.5.1 | Explore and exchange information on provision of reception facilities for oil or other materials recovered from accidents | On-going | Netherlands and Belgium |  |  |
| B.5.2* | Consider future developments (2030) in maritime activities and the potential impact on the Bonn Agreement. This consideration would look at activities; inter alia, the increasing size of vessels, renewable energy, offshore oil and gas industry, LNG fuels and port expansions | Ongoing | Netherlands |  |  |
| B.6.1* | Exchange information on national levels of response capacity tacking into account the results of BE-AWARE | Activity undertaken when required | Contracting Parties concerned |  |  |

Actions in relation to Strategic Aim C (Response):

| Product | Description | Target date | Lead | Progress | Status |
| --- | --- | --- | --- | --- | --- |
| C.1.1 | Exchange information on lessons learned on incidents. | OTSOPA BONN | Contracting Parties |  |  |
| C.2.1 | Maintain an efficient system for the management of requests for and offers of assistance utilising the Marine Pollution Common Emergency Communication and Information System (CECIS MP) of the European Commission | On-going | European Union |  |  |
| C.2.2 | Maintain and keep up to date joint response plans to maritime incidents (DENGERNETH Plan, MANCHEPLAN, Quadripartite Zone Plan, NORBRIT Plan, UK and Ireland MOU) | Activity undertaken when required | Contracting Parties concerned |  |  |
| C.2.3 | Maintain information exchange on national wildlife response systems and update the Chapter on wildlife response in the Counter Pollution Manual | On-going | Contracting Parties; supported by Sea Alarm |  |  |
| C.2.4* | Develop specific response strategies for pollution incidents in relation to new maritime activities (e.g. wind farms) | [2017 or 2018] | Germany and Netherlands |  |  |
| C.3.1 | Initiate research and development: on accidents at night, in bad visibility and under bad weather conditions; accidents involving heavy oil and chemical accidents, possibly through externally funded projects; on response technologies, equipment and other operational means, in particular on integrated surveillance sensors, oil spill drift forecasting and response technologies | On-going | Sweden and Norway |  |  |
| C.3.2* | Promote research on HNS response technologies and operational decision support tools taking into account lessons learned from past projects | 2017 | France, Germany, Belgium and the European Union |  |  |
| C.4.1* | Follow up of the response actions of the BE-AWARE I and II projects in line with the Implementation Plan | In line with implementation plan | Contracting Parties |  |  |
| C.4.2* | Consideration and development of a project proposal for a regional risk assessment for HNS | 2016/2017 | Contracting Parties and Secretariat |  |  |
| C.5.1* | Promote networking with other Regional Agreements through the exchange of experts and observers in response operations | Activity undertaken when required | Contracting parties |  |  |

Actions in relation to Strategic Aim D (Organisation)

| Product | Description | Target date | Lead | Progress | Status |
| --- | --- | --- | --- | --- | --- |
| D.1.1* | Review the political, economic, organisational, technical and legal changes being faced by the organisation, based on the outcome of a SWOT analysis, taking into account the outcomes of the BE-AWARE Projects | 2017 | Netherlands and Secretariat |  |  |
| D.2.1* | Review and, if necessary, consider updates to the Bonn Agreement mandate, including inter alia consideration of the scope and coverage of the Bonn Agreement | 2018 | Secretariat and Contracting Parties |  |  |
| D.3.1* | Organise a Bonn Agreement Ministerial meeting in 2019 to mark the 50th anniversary of the agreement, Review and consider the Bonn Agreement’s mandate based on the outcome of the SWOT analysis | 2019 | Germany and Secretariat |  |  |

Norway is not a member of the European Union. Norway contributes on the basis of equivalent national legislation and EU legislation by which they are bound as member of the European Economic Area (EEA).

Norway is not a member of the European Union. Norway contributes on the basis of equivalent national legislation and EU legislation by which they are bound as member of the European Economic Area (EEA).